## Gantt Chart
ACTIVITIES | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4
| WK 1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16
| Jan 2 - 6 | Jan 9 - 13
Context Setting | bar: Month 1 WK 1
Risk Assessment | bar: Month 1 WK2 to Month 1 WK3
Gap Assessment | bar: Month 1 WK4 to Month 2 WK5
Design & Dcoumentation | bar: Month 2 WK6 to Month 2 WK8
Implementation | bar: Month 3 WK9 to Month 3 WK12
Internal Audit | bar: Month 4 WK13 to Month 4 WK14
Certification & Closure | bar: Month 4 WK15 to Month 4 WK16

## Project Activities
Phase | Activities | Start Date | End Date | Effort ( in Days) | Actor | Owner | RAG Status | Jan 2 - 6 |  |  |  |  | Jan 9 - 13
1 | Context Setting | 2023-01-02 | 2023-01-06 | 5 |  |  |  | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
| Kick off meeting | 02-01-2023 | 02-01-2023 | 1 | CF, <Name Of The Org.> | bar: Jan 2 - 6 M
| Project plan finalization | 02-01-2023 | 02-01-2023 |  | <Name Of The Org.> | bar: Jan 2 - 6 M
| Identification of Interested parties (key stakeholders) & their needs and expectations from the ISMS contexts | 03-01-2023 | 03-01-2023 | 1 | CF, <Name Of The Org.> | bar: Jan 2 - 6 T
| ISMS Organizational Structures finalization (Steering Committee, Key roles, Risk Owners, Internal Auditors, Coordinators, Core committee etc.) | 03-02-2023 | 03-02-2023 |  | CF, <Name Of The Org.> | bar: Jan 2 - 6 T
| Finalization of the ISMS Scope, Objectives | 03-02-2023 | 03-02-2023 |  | CF, <Name Of The Org.> | bar: Jan 2 - 6 T
| Developing of the Risk Assessment Methodology | 04-02-2023 | 04-02-2023 | 2 | CF | bar: Jan 2 - 6 W
| Organizations Context setting for ISMS | 04-01-2023 | 05-01-2023 |  | CF, <Name Of The Org.> | bar: Jan 2 - 6 W to Jan 2 - 6 T
| Gap Analysis Schedule finalization & communication | 05-01-2023 | 05-01-2023 |  | CF | bar: Jan 2 - 6 T
| Risk Assessment Schedule finalization & communication | 05-01-2023 | 05-01-2023 |  | CF | bar: Jan 2 - 6 T
| Review & signoff of Risk Assessment Methodology | 05-01-2023 | 05-01-2023 |  | CF, <Name Of The Org.> | bar: Jan 2 - 6 T
| Phase Signoff | 06-01-2023 | 06-01-2023 | 1 | <Name Of The Org.> | bar: Jan 2 - 6 F
2 | Risk Assessment |  |  | 10
| Risk Assessment Workshop |  |  |  | CF
| Regular coordination and guidance for Risk Owners for completion of Risk Assessment |  |  |  | CF, <Name Of The Org.>
| Regular coordination and guidance for Risk Owners for completion of Risk Treatment |  |  |  | CF, <Name Of The Org.>
| Statement of Applicability (SOA) creation |  |  |  | CF
| Final Risk Assessment & Treatment Plan acceptance & signoff |  |  |  | <Name Of The Org.>
3 | Gap Assessment |  |  | 10
| Test of design of information security in <Name Of The Org.> (Documentation Review) |  |  |  | CF, <Name Of The Org.>
| Test of Practice of information security vis a vis ISO 27001 (interviews & evidence collection) |  |  |  | CF, <Name Of The Org.>
| Development of gap assessment report |  |  |  | CF
| Presentation of gap assessment report |  |  |  | CF
| Phase Signoff |  |  |  | <Name Of The Org.>
4 | Documentation |  |  | 15
| Development of applicable documents: Pack 1 |  |  |  | CF
| Presentation of Pack 1 |  |  |  | CF
| Review of Pack 1 |  |  |  | <Name Of The Org.>
| Development of applicable documents: Pack 2 |  |  |  | CF
| Presentation of Pack 2 |  |  |  | CF
| Review of Pack 2 |  |  |  | <Name Of The Org.>
| Development of applicable documents: Pack 3 |  |  |  | CF
| Presentation of Pack 3 |  |  |  | CF
| Review of Pack 3 |  |  |  | <Name Of The Org.>
| Collection of review feedback (Pack 1, 2, 3) & modification |  |  |  | CF, <Name Of The Org.>
| Final Design and Documentation Phase signoff |  |  |  | <Name Of The Org.>
5 | Implementation |  |  | 20
Role based training of ISMS & controls
Go-live planning coordination
Updated ISMS & GDPR go-live
| Awareness workshops on the following topics: ISMS in <Name Of The Org.> |  |  |  | CF, <Name Of The Org.>
Post go-live guidance in generation and collation of records that verify and demonstrate the working of security controls
Provide guidance to resolve any issues in implementation of controls
| Implementation assistance Phase Signoff |  |  |  | <Name Of The Org.>
6 | Internal Audit |  |  | 10
| Internal Audit Schedule |  |  |  | CF
| Conducting one round of internal audit to review the adequacy of Documents required for ISMS & GDPR certification Effectiveness of controls implemented |  |  |  | CF, <Name Of The Org.>
| Development of internal audit report |  |  |  | CF
| Management Review Co-ordination |  |  |  | <Name Of The Org.>
| Assisting <Name Of The Org.> in planning the closure of non-conformities identified during the internal audit |  |  |  | CF, <Name Of The Org.>
7 | Certification & Closure |  |  | 10
Assisting <Name Of The Org.> during the ISO 27001:2013 external Audit
Remediation suggestions for External NC’s
Final Project signoff
Legend
| <Name Of The Org.> - <Name Of The Org.> Team | RAG Staus
Completed
Work In Progress
Delayed

## Roles (hidden)
Roles
Roles | Actors
| CTPL | [6 empty] | CSPL | [6 empty] | Clik Source | [6 empty] | Org-Wide
| HR | IT | Admin & Facilities | Finance | Accounts | Legal | Procurement | HR | IT | Admin & Facilities | Finance | Accounts | Legal | Procurement | HR | IT | Admin & Facilities | Finance | Accounts | Legal | Procurement
Risk Owner
CISO
ISMS Steering Committee
Interrested Parties
Project Manager
Project Coordinator
Project Core Committee
Project Steering committee